## Test Plan
Requirements:
ID: 1 Register an Account ID: 2 Login to website ID: 3 Create a Post ID: 4 Delete a Post ID: 5 Follow a user ID: 6 Unfollow a user ID: 7 See followed users posts ID: 8 Comment on a post ID: 9 Like a Post ID: 10 Unlike a Post ID: 11 Add post to Reading List ID: 12 Remove from Reading List ID: 13 Check notifications ID: 14 Create a Society ID: 15 Check user profile
Features to be tested:
TC.001: Register an Account TC.002: Login to Website TC.003: Create a Post TC.004: Delete a Post TC.005: Follow a user TC.006: Unfollow a user TC.007: see followed users posts TC.008: Comment on a post TC.009: Like a post TC.010: Unlike a post TC.011: Add post to Reading List TC.012: Remove from Reading List TC.013: Check notifications TC.014: Create a Society TC.015: Check user profile
|  | Purpose: | This set of tests is intended to check main functionality developed
Test Plan Objective: Test the Functionality of the website zoosh
Requirement ID | Sprint | Test Case Ref | Test Case Name | Descriptions | Search Parameters / Instructions | Checks | Expected Result | Actual Result | Results Pass/Fail | Bug # | Comments
1 | 1 | TC.001 | Register an Account | A new user can create their own account on the website | 1. Launch website 2. Click on button "create an account" 3. Enter details 4. See if user is logged in | 1: User enters empty fullname 2. User enter empty username 3. User enters invalid email 4. User enters empty password | If user enters all valid details an account will be created. They should also be redirected to their homepage | Account successfully created. Redirected to home page | Pass | N/A | * Account creation runs at optimal speed. * Redirect to home page is fast
2 | 1 | TC.002 | Login to website | A user who holds an account can login back to the website. | 1. Launch website 2. Enter details 4. See if user is logged in | 1. User enters invalid email, 2. User enters invalid password. | If the user enters the correct details they should be logged in. They should also be redirected to their home page | Succesfully logged in. Redirected to home page. | Pass | N/A | * Redirect to home page is fast.
3 | 2 | TC.003 | Create a Post | Once logged in a user can create a post. | 1. Once logged in. 2. Navigate to home page. 3. Click on button "Write a post" 4. Fill in details as desired. | 1. User enters empty title. 2. User enters empty caption 3. User enters empty content. | Post will be succesfully created. Post can be viewed on user profile. | Post is succesfully created and displays. | pass | N/A | N/A
4 | 2 | TC.004 | Delete a Post | Once a post has been created the user who made the post can delete it from their profile page | 1. Create a post 2. Navigate to your profile page. 3. Click "Delete" on the post. 4. Notice if the post is gone. | 1. User must have atleast one post. | Once the delete button is clicked the post should be deleted. | The post got deleated from the database. | Pass | N/A | N/A
5 | 3 | TC.005 | Follow a user | When logged in a user has the ability to follow another users account. | 1. Provided you are logged in. 2. Navigate to another users profile. 3. Click the follow button. | 1. User must be logged in. | When the user clicks the follow button the page should refresh and "Follow" should change to "Unfollow" Followers counter should change also | A user can succesfully follow another. | pass | N/A | * Load times are fast.
6 | 3 | TC.006 | Unfollow a user | The user has the ability to unfollow a user they already currently follow. | 1. Provided you are following a user. 2. Navigate to the users profile. 3. Click the unfollow button. | 1. User must be following at least one other user. | When the user click the unfollow button the page should refresh and "Unfollow" should change to "follow" Followers counter should change also | A user can succesfully unfollow someone who they currently follow. | Pass | N/A | * Performance of database is working at a high level.
7 | 3 | TC.007 | See followed users posts | When a user follows another user their posts will be available to view on the feed. | 1. Provided you are following a user who has posts. 2. Navigate to the feed page 3. Notice if posts are displaying. | 1. User must be following at least one other user. 2. The user must have at least one post. | When the user follows another user with posts. The posts should display on the feed. | Posts display of the user who you follow. | Pass | N/A | N/A
8 | 4 | TC.008 | Comment on post | The user has the ability to comment on a post. | 1. Navigate to a post. 2. Under the post write a comment. | 1. User must be logged in. | When the user comments on a post the comment will display under the post. | The comment displays under the post. | Pass | N/A | N/A
9 | 4 | TC.009 | Like a post | The user has the ability to like a post. | 1. Navigate to a post. 2. Click on the heart button. | 1. User must be logged in. | When the user clicks on the button the page will refresh and the heart will change to red with the counter updating by one | The heart changed to red and the counter updated by one. | Pass | N/A | N/A
10 | 4 | TC.010 | Unlike a post | The user has the abiliy to unlike a post. | 1. Navigate to a post. 2. Click on the heart button. | 1. User must be logged in. | When the user clicks on the button the page will refresh and the heart will change to white with the counter updating by -1 | The heart changed to white and the counter updated by -1. | Pass | N/A | N/A
11 | 1 | TC.011 | Add post to Reading List | The user has the ability to save a post to their reading list | 1. Navigate to a post. 2. Click on the bookmark button. 3. Navigate to your profile. 4. Click on the bookmark button. 5. View your reading list. | 1. User must be logged in. | When the user clicks on the bookmark button a message will appear saying "Added to your reading list!" When the user views their reading list the post will be there | The post is saved to the reading list and available to view on the reading list page. | Pass | N/A | * Database performance is optimal.
12 | 5 | TC.012 | Remove post from Reading List | The user has the ability to remove a post from | 1. Navigate to the post. 2. Click on the bookmark button. | 1. User must have atleast one post saved in the reading list. | When the user clicks the bookmark icon a message will appear as follows"Removed from your reading list!" Then the post will be removed from the list. | The message "Removed from your reading list!" appeared and the post was removed. | Pass | N/A | N/A
13 | 6 | TC.013 | Check Notifications | When someone comments or likes a user's post they should reveive a notification. | 1. Get another user to follow you or comment/like a post you have created. 2. Navigate to the notifications page. 3. View notifications. | 1. User must get another user to comment/like one of their posts or follow you. | When someone follows you or comments/likes a post the user will reveive a notification. | Notifications working as intended. | Pass | N/A | N/A
14 | 7 | TC.014 | Create a Society | A user has the ability to create a society. | 1. Navigate to the Explore page. 2. Click the button create a community. 3. Enter in required details. | 1. Community name and description must be entered. | When someone creates a society the society should be created and can be viewed on the explore page | Society creation is working at intended. Test society is shown in the explore page. | Pass | N/A | * Society creation is working at a high performance level.
15 | 8 | TC.015 | Check User Profile | A user can see customise their profile. All posts created by the user are shown. Sign out functionality working. | 1. Navigate to your profile. 2. Notice posts created. 3. Edit your profile. 4. Sign out. | 1. User must have at least one post. | When the user tests the functionality of their profile, they should be able to view their profile, edit their profile and sign out. | All functionality working as intended. | Pass | N/A | N/A